# ICEBERG Deal-Review Notes

deal review 7/9 — ICEBERG (boreal compute) — rough notes, sorry, typed live

attending: me, Priya (deployment), Tomas (memory BU), Katie (edge), someone from finance (Raj?)

priya: 2000 gpu = ~25 racks, liquid cooled. site already certified she says?? confirm. deployment window realistically 10-12 wks incl burn-in IF hardware lands by early sept. so PO needs to be signed AUGUST 15 LATEST

tomas — memory modules: validated config exists for that node type. lead time currently 8 wks, improving. says supply is "fine unless they change node SKU late" (flag as risk #1)

katie: fault tolerant edge — austin + rotterdam sites, 99.999 SLA. says our standard edge bundle covers it BUT rotterdam needs EU support contract — legal review needed (risk #2)

finance guy: margin fine, wants milestone billing. board thing on their side oct 1 — plan must be SIGNED before that. actually maya said mid-august for the plan?? use aug 15, matches the PO date anyway

actions (who/when):

priya → draft deployment timeline w/ burn-in phases — by fri 7/17

tomas → confirm memory module supply commitment in writing — 7/24

katie → start legal review EU support (rotterdam) — asap, long pole??

me → scoping call w/ maya + dev okonkwo week of 7/20, then project brief

??? → exec status update for our leadership before scoping call — ME probably

risks so far: late SKU change (memory), EU legal (edge), hardware delivery slip vs aug/sept window, and honestly the oct 1 board date is the real cliff

random: dev okonkwo wants per-node burn-in data. priya says standard report covers it. double check.

next review 7/16

Training scenario. Names and figures are illustrative.